## Slide 1
Dataset Characterization
for Small Language Model Training
Week 4 Progress Report (Feb 5 - Feb 11, 2026)
KeonSoo | UNLV Research Lab

## Slide 2
Research Goal & Context
Original Proposal
Systematically analyze and refine training datasets for Small Language Models by understanding their inherent characteristics. Rather than simply filtering data, deeply understand what different data sources offer.
Current Status
Timeline: Week 4 of 16 (25% complete)
Phase:
Dataset Characterization
Focus:
Understanding dataset properties through multi-dimensional metrics
Key Challenge:
Balancing domain coverage, quality, difficulty, and redundancy under computational constraints

## Slide 3
The Journey: Learning from Failures
Week 1-3: Initial explorations revealed critical constraints
❌ Attempt 1: Graph-Based Classification
Built prerequisite graphs for K-12 curriculum hierarchy. Failed because cross-cutting concepts (e.g., "algebraic geometry") cannot be assigned to single nodes. Graph structure too rigid for multi-domain documents.
❌ Attempt 2: SentenceTransformers Embeddings
Tried using all-MiniLM-L6-v2 for semantic embeddings. HuggingFace model downloads blocked by remote proxy (403 Forbidden). Cannot rely on external model downloads in production environment.
❌ Attempt 3: GPT-2 Perplexity Scoring
Initially planned GPT-2 for text quality measurement. Model download (550MB) failed in remote environment. Even with local cache, GPU requirements too demanding for 200K+ paragraphs.
❌ Attempt 4: Direct Khan Academy API
Tried scraping Khan Academy content directly. API returned 410 Gone (deprecated ~2023). Backup HuggingFace datasets blocked by proxy. Required pivot to Cosmopedia synthetic data.

## Slide 4
The Solution: Pragmatic Trade-offs
Shifted from ideal to achievable — optimizing for remote execution and offline capability
✓ Vector-Based Multi-Label Classification
Replaced graphs with cosine similarity between document vectors and course prototypes. Allows soft assignment: text can be 60% Math + 40% Physics. Inspired by multi-head attention mechanisms.
✓ TF-IDF Instead of Transformers
Used sklearn TfidfVectorizer (300-dim sparse vectors). Works completely offline, no model downloads. Trade-off: lexical similarity vs semantic, but sufficient for domain classification.
✓ Rule-Based Educational Markers
Replaced perplexity with regex pattern matching for educational signals: examples ("for example"), explanations ("because"), structure ("first", "second"). Fast, interpretable, no GPU needed.
✓ HuggingFace Cosmopedia Dataset
Used Cosmopedia's Khan Academy subset (18,764 entries). Synthetic but preserves taxonomy structure. Dual download strategy: datasets library → parquet API fallback for proxy resilience.

## Slide 5
Final Pipeline: 5 Metrics Across 3 Steps
STEP 1
Extract Khan Taxonomy
TF-IDF vectors for 100 course-level prototypes
STEP 2a
Build Corpus Index
MinHash LSH + TF-IDF matrix (15GB)
STEP 2
Compute 5 Metrics
Per-paragraph analysis (479MB output)
Domain Coverage
Top-5 concepts
with scores
Quality
Educational
markers
Difficulty
Flesch-Kincaid
+ lexical diversity
Redundancy
MinHash +
TF-IDF similarity
Perplexity
GPT-2 log-loss
(optional)
STEP 3
Build Interactive Dashboard

## Slide 6
Results: Dataset Analysis Complete
18,764
Khan Academy Concepts
Math (82%), Science (9%), Social Studies (7%)
~100,000
Tiny-Textbooks Docs
42 batches, synthetic educational content
Generated Outputs
●
khan_taxonomy.json
66 MB
100 course prototypes
●
corpus_index.pkl
15 GB
MinHash + TF-IDF index
●
khan_analysis.jsonl
156 MB
Paragraph-level metrics
●
tiny_textbooks_analysis.jsonl
323 MB
Paragraph-level metrics

## Slide 7
Key Technical Decisions
What we learned from 2 weeks of iteration
Vector-Based > Graph-Based
Why: Multi-label soft assignment allows documents to span multiple domains probabilistically
Impact: Captures cross-cutting concepts like "algebraic geometry" (Math 60% + Geometry 40%)
TF-IDF > SentenceTransformers
Why: Remote execution requires offline capability; no external model downloads
Impact: Trade lexical for semantic similarity, but sufficient for domain classification
Rule-Based > Perplexity
Why: Educational markers (examples, explanations) detectable via regex without GPU
Impact: Fast, interpretable quality metrics; validates synthetic data educational structure
Modular Pipeline > Monolithic
Why: Each step produces reusable artifacts; failures don't cascade
Impact: Can iterate on metrics independently; easy to add new dimensions

## Slide 8
Next Steps (Week 5-6)
Immediate (This Week)
✓ Dashboard Generation
Visualize domain distribution, quality metrics
Manual Validation (100 samples)
Compute precision/recall for domain classification
Threshold Tuning
Optimize MIN_SIMILARITY (currently 0.1)
Short-Term (2 Weeks)
Full Dataset Processing
Complete Tiny-Textbooks (all 42 batches)
Dataset Comparison Analysis
Khan vs Tiny-Textbooks quality/coverage
Expand to Additional Sources
Wikipedia, C4 sampled subsets

## Slide 9
Summary: 2 Weeks of Iteration
✓ Failed fast: Graph-based → Vector-based, SBERT → TF-IDF, Perplexity → Rules
✓ Built pragmatically:
Prioritized remote execution, offline capability, modular design
✓ Delivered metrics:
5 dimensions (Domain, Quality, Difficulty, Redundancy, Perplexity)
✓ Analyzed scale:
~200,000 paragraphs, 479 MB output, ready for dashboard visualization
Next: Validate, tune, expand to larger corpora